## Sprint
|  |  |  | Week #1 (10 hrs / week) |  |  |  | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 5) | D1 | D2 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28
|  |  |  | 200 | 190 | 180 | 170 | 161 | 152 | 143 | 134 | 125 | 116 | 107 | 99 | 91 | 83 | 75 | 67 | 59 | 51 | 44 | 37 | 30 | 23 | 16 | 9 | 0 | Ideal Burndown
|  |  | 212 | 198 | 191 | 182 | 173 | 156 | 147 | 138 | 132 | 127 | 123 | 115 | 109 | 102 | 87 | 83 | 70 | 64 | 52 | 39 | 27 | 12 | 5 | 3 | 1 | 0 | Remaining Hrs (Total)
Game design | Game theme design | He Fu | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Game basic structure design | He Fu | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Character (Hawking) design | Dan Lu | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Character (Darwin) design | Yifan Liang | 5 | 5 | 4 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Character (Newton) design | Li Zhang | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Character (Tesla) design | Zhiye Chen | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Character (Dr.P) design | He Fu | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base structure | Opening | Yifan Liang | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ending | Yifan Liang | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main menu | He Fu | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Base player/enermy/bullet class | He Fu | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Character Hawking skills | Base attack | Dan Lu | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill1 | Dan Lu | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill2 | Dan Lu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ultimate skill | Dan Lu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Character Darwin skills | Base attack | Yifan Liang | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill1 | Yifan Liang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill2 | Yifan Liang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ultimate skill | Yifan Liang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Character Newton skills | Base attack | Li Zhang | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill1 | Li Zhang | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill2 | Li Zhang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ultimate skill | Li Zhang | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Character Tesla skills | Skill1 | Zhiye Chen | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill2 | Zhiye Chen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill3 | Zhiye Chen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill4 | Zhiye Chen | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ultimate skill | Zhiye Chen | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Character Dr.P skills | Base attack | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill1 | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill2 | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ultimate skill | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enemy design | Enemy 1 design | Dan Lu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Enemy 2 design | Li Zhang | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Boss design | He Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enemy programming | Enemy 1 | Dan Lu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Enemy 2 | Dan Lu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Enemy stage | Li Zhang | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| Boss stage 1 | He Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Boss stage 2 | Dan Lu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0
World design | World | He Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Post-effect | Character (Hawking) post-effect | Dan Lu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0
| Character (Darwin) post-effect | Yifan Liang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 2 | 1 | 0
| Character (Newton) post-effect | Li Zhang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0
| Character (Tesla) post-efffect | Zhiye Chen | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 1 | 0 | 0 | 0 | 0
| Character (Dr.P) post-effect | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ult cutscene | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| Boss post-effect | He Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| BGM | Li Zhang | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UI | He Fu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
| Opening logo | He Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Choose and implement design pattern | Iterator pattern | Zhiye Chen | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Strategy pattern | Yifan Liang | 5 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Factory method pattern | Dan Lu | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| State pattern | Li Zhang | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Observer pattern | He Fu | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team:
Dan Lu | 10 hours / Week
He Fu | 10 hours / Week
Li Zhang | 10 hours / Week
Yifan Liang | 10 hours / Week
Zhiye Chen | 10 hours / Week
Total Available Hours During Sprint: | 200

## Weekly Stand-Up
Team One Punch Man, Sprint #1
Team Member Name | Dan Lu | He Fu | Li Zhang | Yifan Liang | Zhiye Chen
What I did since the last weekly scrum: | Design Start Screen | Design game theory | Design player Newton | Design Start and Ending Screen | Design player: Tesla
| Design Hawking player | Design game basic structure |  | Design Darwin Player | Design thunder effect
Design player: Mr.P
What I plan to do this week: | Implement hawking basic attack | Coding for basic structure | Coding for Newton basic attack | Implement Darwin basic attack | Player Tesla base and state
| Desigin Hawking skill 1,skill 2 | Coding for player: Mr.P |  | Design Darwin skill 1 & 2 | Tesla skill 1, 2, 3, 4
Shocked buff effect
What blockers I have: | set image size adjustable | None | Can not make background of image transparent | Resize the image to fit the world | Basic actor and world
XP Core Values: | Courage: focus on only what is required | Communication: Our team discussed and made decisions about the game theory together during our weekly face-to-face meeting. | Respect: respects each other as a valued team member.Apple object can not move around Newton in a circle | Simplicity: Design only what is in the requirements. | Feedback: Unit tests tell the developers the status of the system.
Team One Punch Man, Sprint #2
Team Member Name | Dan Lu | He Fu | Li Zhang | Yifan Liang | Zhiye Chen
What I did since the last weekly scrum: | Improve Hawking screen attack | Create basic classes | Create Newton Object | Finish Darwin player design | Adding iterator pattern
| Adding decorator pattern | Adding observer pattern | Design Newton skills | Adding strategy pattern | improve thunder effect
| Hawking skill1, 2 | Mr.P basic attack |  | Finish Darwin skill 1&2 | Tesla skill 1, 2, 3, 4
What I plan to do this week: | Design hawking ultra skill | Finish Mr.P | Finish Newton | Design Darwin ultra skill | Coding for skill ult
| Code for ultra skill |  |  | Polish Darwin skill 1&2 | Improve Tesla attack state
Improve enemy buff state
What blockers I have: | Basic attack effects | None | Apple object can not move around Newton in a circle | Player cannot move using Mac | improvement of base
XP Core Values: | Courage: communicate and accept feedback | Communication: Our team talked about the features of each character and discussed about solutions for problems we met. | Respect: Everyone contributes value such as enthusiasm | Simplicity: Program only what is in the design. | Feedback: Unit tests tell the developers the status of the system.
Team One Punch Man, Sprint #3
Team Member Name | Dan Lu | He Fu | Li Zhang | Yifan Liang | Zhiye Chen
What I did since the last weekly scrum: | Hawking ultra skill | Mr.P skill 1 | Newton skill 1 | Improve Darwin skill 1&2 | Tesla skill ult
| Imporive skill 1, 2 | Mr.P skill 2 | Newton skill 2 | Implement Darwin ultra skill | Finish Tesla base
|  | Mr.P ult | Newton ult | Figure out player moving on Mac | Finish buff base
What I plan to do this week: | Add enemies to Mobstage | Dr.P post-effect | World Stage 1 | Finish Darwin ultra skill | Tesla post-effect
| Add screen attack effect | Ult-cutscence | Game BGM |  | Tesla skill sound
UI
What blockers I have: | None | None | None | None | None
XP Core Values: | Courage: adapt to changes whenever they happen | Communication: Our team members showed each other their characters' features and discussed about the common UI and ult-cutscence design. | Respect: respect the expertise of each team member. | Simplicity: Test only what is in the requirements. | Feedback: Frequent releases enable performance acceptance tests and provide feedback.
Team One Punch Man, Sprint #4
Team Member Name | Dan Lu | He Fu | Li Zhang | Yifan Liang | Zhiye Chen
What I did since the last weekly scrum: | Imporve attack effect | Dr.P post-effect | world stage 1 | Darwin post-effect | Tesla post-effect
| Code for enemy in mobstag | Ult-cutscence | BGM for world stage 1 | Improve Darwin skills transactions | Tesla skill sound
UI
XP Core Values: | Courage: adapt to changes whenever they happen | Communication: Our team merged the whole project during face-to-face meeting, played it and talked about the presentation order on demo day. | Respect: respects the right of team members to accept the responsibility and receive authority over their own work. | Simplicity: Test only what is in the requirements. | Feedback: estimate the time required to deliver the changes, to set the expectations。

## UI Wireframes
Opening | Menu | Player UI
Boss UI | Player and Mobs | Pass/Dead

## UML Analysis Models
Activity Diagram | Usecase Overview Diagram
Use Case Specification Sequence Diagram for player basic bullet attack

## Domain Model Diagram
Class Diagram