## Sprint
|  |  |  | Week #1 (10 hrs / week) |  |  |  | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 5) | D1 | D2 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28
|  |  |  | 200 | 190 | 180 | 170 | 161 | 152 | 143 | 134 | 125 | 116 | 107 | 99 | 91 | 83 | 75 | 67 | 59 | 51 | 44 | 37 | 30 | 23 | 16 | 9 | 0 | Ideal Burndown
|  |  | 43 | 44 | 42 | 40 | 36 | 31 | 29 | 28 | 27 | 24 | 21 | 22 | 25 | 20 | 17 | 17 | 12 | 12 | 14 | 10 | 5 | 4 | 1 | 1 | 1 | 1 | Remaining Hrs (Total)
Game design | Game theme design | He Fu | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Game basic structure design | He Fu | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Character (Hawking) design | Dan Lu |  | 2018-04-04: 3; 2018-04-05: 2; 2018-04-06: 3; 2018-04-07: 2
| Character (Darwin) design | Yifan Liang |  | 2018-04-04: 2; 2018-04-05: 3; 2018-04-06: 2; 2018-04-07: 3
Character (3 enter your character name) design
Character (4 enter your character name) design
| Character Dr.P design | He Fu | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base structure | Opening
Ending
Main menu
| Base player/enermy/bullet class | He Fu | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Character (1 Hawking) skills | Base attack | Dan Lu |  | 2018-04-08: 0; 2018-04-09: 0; 2018-04-10: 0; 2018-04-11: 1; 2018-04-12: 2; 2018-04-13: 0; 2018-04-14: 0; 2018-04-15: 0; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 0
| Skill1 | Dan Lu |  | 2018-04-08: 1; 2018-04-09: 0; 2018-04-10: 1; 2018-04-11: 0; 2018-04-12: 0; 2018-04-13: 1; 2018-04-14: 0; 2018-04-15: 1; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 0
| Skill2 | Dan Lu |  | 2018-04-08: 0; 2018-04-09: 1; 2018-04-10: 0; 2018-04-11: 1; 2018-04-12: 0; 2018-04-13: 0; 2018-04-14: 1; 2018-04-15: 0; 2018-04-16: 0; 2018-04-17: 1; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 0
| Ultimate skill | Dan Lu |  | 2018-04-08: 0; 2018-04-09: 0; 2018-04-10: 0; 2018-04-11: 0; 2018-04-12: 0; 2018-04-13: 0; 2018-04-14: 1; 2018-04-15: 0; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 3; 2018-04-19: 0; 2018-04-20: 1; 2018-04-21: 0
Character (2 Darwin) skills | Base attack | Yifan Liang |  | 2018-04-08: 2; 2018-04-09: 1; 2018-04-10: 0; 2018-04-11: 0; 2018-04-12: 0; 2018-04-13: 0; 2018-04-14: 0; 2018-04-15: 0; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 0
| Skill1 | Yifan Liang |  | 2018-04-08: 0; 2018-04-09: 1; 2018-04-10: 2; 2018-04-11: 0; 2018-04-12: 0; 2018-04-13: 0; 2018-04-14: 0; 2018-04-15: 0; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 0
| Skill2 | Yifan Liang |  | 2018-04-08: 0; 2018-04-09: 0; 2018-04-10: 1; 2018-04-11: 2; 2018-04-12: 0; 2018-04-13: 0; 2018-04-14: 0; 2018-04-15: 0; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 0
| Ultimate skill | Yifan Liang |  | 2018-04-08: 0; 2018-04-09: 0; 2018-04-10: 0; 2018-04-11: 0; 2018-04-12: 1; 2018-04-13: 0; 2018-04-14: 0; 2018-04-15: 2; 2018-04-16: 3; 2018-04-17: 1; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 0
Character (3 enter your character name) skills | Base attack
Skill1
Skill2
Ultimate skill
Character (4 enter your character name) skills | Base attack
Skill1
Skill2
Ultimate skill
Character Dr.P skills | Base attack | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill1 | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Skill2 | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ultimate skill | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enermy design | Enermy 1 design | Dan Lu | 3 | 2018-04-04: 3; 2018-04-05: 3; 2018-04-06: 3
Enermy 2 design
Boss design
Enermy programming | Enermy 1 | Dan Lu
| Enermy 2 | Dan Lu
Boss stage 1
Boss stage 2
World design | World
Post-production | Character (Hawking) post-effect | Dan Lu |  | 2018-04-15: 4; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 0
| Character (Darwin) post-effect | Yifan Liang |  | 2018-04-15: 0; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 0; 2018-04-19: 0; 2018-04-20: 0; 2018-04-21: 4
Character (3 enter your character name) post-effect
Character (4 enter your character name) post-effect
| Character Dr.P post-effect | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ult cutscene | He Fu | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
Boss post-effect
BGM
| UI | He Fu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
Opening logo
Choose and implement design pattern | 1 pattern
| Strategy pattern | Yifan Liang |  | 2018-04-22: 2; 2018-04-23: 1; 2018-04-24: 3; 2018-04-25: 1; 2018-04-26: 1; 2018-04-27: 1; 2018-04-28: 1
3 pattern
4 pattern
| Observer pattern | He Fu | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team:
Dan Lu | 10 hours / Week
He Fu | 10 hours / Week
Li Zhang | 10 hours / Week
Yifan Liang | 10 hours / Week
Zhiye Chen | 10 hours / Week
Total Available Hours During Sprint: | 200

## Weekly Stand-Up
Team One Punch Man, Sprint #1
Team Member Name | Dan Lu | He Fu | Li Zhang | Yifan Liang | Zhiye Chen
What I did since the last weekly scrum: | Design Start Screen | Design game theory | Design player Newton
| Design hawking player structure | Design game basic structure
Design player: Mr.P
What I plan to do this week: | Coding for hawking basic attack | Coding for basic structure | Coding for Newton basic attack
Coding for player: Mr.P
What blockers I have: | None | None | None
XP Core Values: | Communication: Our team discussed and made decisions about the game theory together during our weekly face-to-face meeting. | Communication: Our team discussed and made decisions about the game theory together during our weekly face-to-face meeting.
Team One Punch Man, Sprint #2
Team Member Name | Dan Lu | He Fu | Li Zhang | Yifan Liang | Zhiye Chen
What I did since the last weekly scrum: | Create player basic classes | Create basic classes | Create Newton Object
| design player skills | Adding observer pattern | Design Newton skills
Mr.P basic attack
What I plan to do this week: | Finish basic logic for player | Finish Mr.P | Finish Newton
What blockers I have: | None | None
XP Core Values: | Communication: Our team talked about the features of each character and discussed about solutions for problems we met. | Communication: Our team talked about the features of each character and discussed about solutions for problems we met.
Team One Punch Man, Sprint #3
Team Member Name | Dan Lu | He Fu | Li Zhang | Yifan Liang | Zhiye Chen
What I did since the last weekly scrum: | Hawking skill 1 | Mr.P skill 1 | Newton skill 1
| Hawking skill 2 | Mr.P skill 2 | Newton skill 2
|  | Mr.P ult | Newton ult
What I plan to do this week: | Hawking ult skill | Dr.P post-effect | World Stage 1
| basic attack effects | Ult-cutscence | Game BGM
UI
What blockers I have: | None | None
XP Core Values: | Communication: Our team members showed each other their characters' features and discussed about the common UI and ult-cutscence design. | Communication: Our team members showed each other their characters' features and discussed about the common UI and ult-cutscence design.
Team One Punch Man, Sprint #4
Team Member Name | Dan Lu | He Fu | Li Zhang | Yifan Liang | Zhiye Chen
What I did since the last weekly scrum: | Hawking ult skill | Dr.P post-effect | world stage 1
| attack effects | Ult-cutscence | BGM for world stage 1
| coding for world enermies | UI
XP Core Values: | Communication: Our team merged the whole project during face-to-face meeting, played it and talked about the presentation order on demo day. | Communication: Our team merged the whole project during face-to-face meeting, played it and talked about the presentation order on demo day.

## UI Wireframes
Opening | Menu | Player UI
Boss UI | Player and Mobs | Pass/Dead